## Sheet1
Asset | Threat | Likelihood | Impact | Risk | Mitigation
Database | SQL Injection | High | High | Critical | Perform input validation and make use of an ORM
System Availability | SQL Injection | Medium | High | High | Implement rate limiting and Query timeouts
Application (Nestjs Backend) | SQL Injection | High | High | Critical | Enforce input validation, use ORM to structure schema and connect to DB
Authentication Module | SQL Injection | High | High | Critical | Refute raw SQL in login logic, implement account lockout